## NPS 24-25
Site ID | Region | Engg. Subregion | DISCO | Tagged COA Rollout Year | AC Mode | COA | CW Vendor | City | Tehsil | District | Address | Site Status | CW KO | CW RFI | CP Applied Date | CP DN issued Date | CP DN Amount (Cap_Sec) | CP DN paid Date | CP Installation Date | TCP | PCP | CP Installed (Type) | Status | Tentative Timelines
50712 | North | N2 | PESCO | Y2024 | New-Self | 2024-10-31 20:01 | S&S | Peshawar Pda Hyatabad | Peshawar | Peshawar | Roof Top Rmi Hospital Hayatabad, Peshawar | On-Air | 2023-05-18 | 2023-05-18 |  |  |  |  | Single Phase on 22nd Feb 25
50965 | North | N3 | PESCO | Y2024 | New-Self | 2024-06-30 | S&S | Abbottabad | Abbottabad | Abbottabad | Gali, Dobather Rd, Abbottabad | On-Air | 2023-11-23 | 2023-11-28 | 2023-12-19 | 2023-12-19 | 80000 | 2023-12-19 | 2023-12-30 |  |  | 3 Phase PP only | Closed
51179 | North | N2 | PESCO | Y2024 | New-Self | 2024-11-20 22:54 | S&S | Peshawar Pda Hyatabad | Peshawar | Peshawar | Sector D 1, Street 1, Phase-1 Hayatabad | On-Air | 2023-12-02 | 2023-12-10 | 2023-12-19 | 2023-12-19 | 80000 | 2023-12-19 | 2023-12-30 |  |  | 3 Phase PP only | Closed
51227 | North | N1 | IESCO |  | New-Self | 2024-12-31 18:30 | Highrise | Wah+Texila | Taxila | Wah+Taxila | New City Wah Cantt, Wah Cantt, Rawalpindi | On-Air | 2024-02-20 | 2024-04-02 | 2024-03-09 | 2024-03-19 | 889757 | 2024-03-27 | 2024-04-19 |  |  | 3 phase meter with 25KVA PMT | Closed
51228 | North | N1 | IESCO |  | New-Self | 2024-12-29 23:20 | Highrise | Wah+Texila | Taxila | Wah+Taxila | GT Rd,Asifabad wah rawalpindi | On-Air | 2024-02-21 | 2024-03-29 | 2024-03-28 | 2024-05-06 | 949626 | 2024-04-16 | 2024-06-27 |  |  | 3 phase meter with 25KVA PMT | Closed
51230 | North | N1 | IESCO |  | New-Self |  | Highrise | Wah+Texila | Taxila | Wah+Taxila | Barrier 3 Bus Stop,G.T Road, Wah, Rawalpindi | On-Air | 2024-03-07 | 2024-04-22 |  |  |  |  | 2024-04-22 |  |  | Authority site DN NA | Closed
51555 |  | N3 |  |  | Self |  | Highrise | Mansehra | Mansehra |  | Village Dhangri, Tehsil & District Mansehra | On-Air | 2024-04-17 | 2024-05-24 | 2024-05-24 | 2024-05-31 | 866,313 | 2024-06-04 | 2024-06-14 |  |  | Permanent Power | Closed
51560 | North | N2 | PESCO | Y2024 | New-Self | 2024-07-30 17:24 | Highrise | - | Nowshera | Nowshera | R-Main Tower. Main Nowshehra Cantt | On-Air | 2024-04-19 | 2024-05-24 | 2024-04-25 | 2024-05-03 | 837,270 | 2024-05-15 | 2024-05-25 |  |  | Permanent Power | Closed
51769 | North | N2 | PESCO | Y2024 | New-Self | 2024-06-30 | S&S | Peshawar | Peshawar | Peshawar | Askari 2,Peshawar Cantt | On-Air | 2024-04-25 | 2024-04-26 |  |  |  |  | Site Off | Site Off | Site Off | Site Off
51794 | North | N2 | PESCO | Y2024 | New-Self | 2024-08-31 22:51 | S&S | Peshawar | Peshawar | Peshawar | Hostel # 3, UET Peshawar. | On-Air | 2024-04-26 | 2024-06-14 | 2024-08-20 | 2024-08-21 | 1145988 | 2024-08-23 | NOC Pending at CMPak End |  |  | 3 phase meter with 25KVA PMT
51851 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-14 | Highrise | 0 | Islamabad | Islamabad | Sector C DHA Phase II, Islamabad | On-Air | 2024-04-26 | 2024-06-12 | 2024-06-05 | 2024-06-11 | 41150 | 2024-06-13 | Off Grid |  |  | 3 Phase PP only | Off Grid
52024 | North | N1 | IESCO | Y2024 | New-Self | 2024-09-30 23:26 | Highrise | Islamabad | Islamabad | Islamabad | Service Rd W, G 11/1 G-11, Islamabad | On-Air | 2024-05-09 | 2024-06-07 | 2024-07-15 | 2024-07-15 | 417219 | 2024-07-18 | CP will be installed on 5 Mar 25 |  |  | 3 phase meter with 25KVA PMT
52025 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Islamabad | Islamabad | Islamabad | Along Nala, Near Lal masjid, G-6/4, Islamabad. | On-Air | 2024-05-14 | 2024-06-08 | 2024-07-02 | 2024-07-02 | 661,525 | 2024-07-10 | Off Grid |  |  | Permanent Power | Off Grid
52090 | North | N1 | IESCO | Y2024 | New-Self | 2024-05-29 | S&S | Islamabad | Islamabad | Islamabad | I-9/3 I-9, Islamabad, | On-Air | 2024-05-16 | 2024-06-11 | 2024-05-27 | 2024-05-31 | 674,600 | 2024-06-05 | Off Grid |  |  | Permanent Power | Off Grid
52191 | North | N1 | IESCO |  | New-Self | 2024-12-23 10:36 | Highrise | Rawalpindi | Rawalpindi | Rawalpindi | Officers Ward, CMH, Rawalpindi. | On-Air | 2024-05-17 | 2024-06-24 | 2024-06-11 | 2024-06-12 | 795620 | 2024-07-02 | Off Grid |  |  | 3 phase meter with 25KVA PMT | Off Grid
52295 | North | N2 | PESCO | Y2024 | New-Self | 2024-09-30 20:12 | S&S | Peshawar | Peshawar | Peshawar | Shami Road Peshawar | On-Air | 2024-05-20 | 2024-06-10 | 2024-05-29 | 2024-06-05 | 831,367 | 2024-06-07 | Off Grid |  |  | Permanent Power | Off Grid
52479 | North | N2 | PESCO | Y2024 | New-Self | 2024-10-31 19:06 | Highrise | Peshawar Pda Hyatabad | Peshawar | Peshawar | Phase 4 Hayatabad | On-Air | 2024-05-21 | 2024-06-13 | 2024-06-07 | 2024-06-07 | 862,317 | 2024-06-20 | CP will be installed on 5 Mar 25 |  |  | Permanent Power
52572 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Rawalpindi | Rawalpindi | Rawalpindi | Lane 4, D-Block, Usman Block Safari Valley, Phase 8 Bahria Town, Rawalpindi | On-Air | 2024-05-22 | 2024-06-06 | 2024-05-24 | 2024-05-24 | 70,150 | 2024-05-29 | COW Site |  |  | Permanent Power | Closed
52583 | North | N3 | IESCO |  | New-Self | 2025-01-03 16:49 | S&S | Haripur_Rural | Haripur | Haripur | Afghan Refugee Camp, Haripur | On-Air | 2024-05-23 | 2024-06-24 | 2024-05-31 | 2024-07-04 | 2966840 | 2024-07-29 |  |  |  |  | Pending
52590 | North | N2 | PESCO | Y2024 | New-Self | 2024-12-06 | Highrise | Peshawar | Peshawar | Peshawar | Aloocho Bagh, Burj Nasir Peshawar. | On-Air | 2024-05-23 | 2024-06-08 | 2024-07-08 | 2024-07-09 | 917712 | 2024-07-12 |  |  |  |  | Pending
52591 |  | N2 |  |  | Self |  | Highrise | Peshawar Pda Hyatabad | Peshawar |  | Peshawar | CW Kick-off Done | 2024-05-24 | [5 empty] | NOC Pending at CMPak End | NOC pending at CMPak End | NOC pending at CMPak End | NOC pending at CMPak End
52604 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Islamabad_Rural | Islamabad | Islamabad | Near Road 4, Sector C, Bahria Enclave, Islamabad | On-Air | 2024-05-29 | 2024-06-14 | 2024-07-12 | 2024-07-12 | 147000 | 2024-07-12 | TSS Peending |  |  | 3 Phase PP only
52676 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-30 10:17 | S&S | Kabal | 0 | Swat | Shan Road, Kanju Swat | On-Air | 2024-05-30 | 2024-06-28 | [8 empty] | Pending
52690 | North | N1 | IESCO | Y2024 | New-Self | 2023-12-19 20:18 | S&S | Fateh Jang_Rural | Fateh Jang | Islamabad | Airport Parking, Islamabad Gandhara International Airport Islamabad | On-Air | 2024-05-30 | [9 empty] | Pending
52691 | North | N1 | IESCO | Y2024 | New-Self | 2023-11-30 18:08 | S&S | Fateh Jang_Rural | Fateh Jang | Islamabad | Airport Parking, Islamabad Gandhara International Airport Islamabad | On-Air | 2024-05-31 | 2024-06-27 | 2024-07-01 | 2024-07-19 | 1549600 | 2024-07-31 | 2024-09-03 |  |  | 3 phase meter with 25KVA PMT | Closed
52742 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | mardan | Mardan | Mardan | Sector K Sheikh Maltoon Town, Mardan | On-Air | 2024-06-03 | 2024-06-13 | 2024-06-25 | 2024-06-26 | 50000 | 2024-06-26 | 2025-03-23 |  | Yes | 3 Phase | Closed
52763 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 18:02 | Highrise | Malakand | Malakand | Malakand | Batkhela, Malakand | On-Air | 2024-06-03 | 2024-06-14 | 2024-06-25 | 2024-06-26 | 50000 | 2024-06-26 | 2024-06-29 |  |  | 3 Phase PP only | Closed
52979 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 20:13 | S&S | Mansehra | Mansehra | Mansehra | Dhangri, Mansehra | On-Air | 2024-06-03 | 2024-06-13 | 2024-06-25 | 2024-06-26 | 50000 | 2024-06-26 | 2024-06-29 |  |  | 3 Phase PP only | Closed
53150 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 17:21 | S&S | Swabi_Rural | Swabi | Swabi | Hill Top Kaala, Swabi | On-Air | 2024-06-03 | 2024-06-14 | 2024-06-25 | 2024-06-26 | 60000 | 2024-06-26 | 2024-06-29 |  |  | 3 Phase PP only | Closed
53173 | North | N2 | PESCO | Y2024 | New-Self | 2024-10-31 19:20 | Highrise | Peshawar Pda Hyatabad | Peshawar | Peshawar | Nawab Market, Phase 6 Hayatabad, Peshawar | On-Air | 2024-06-04 | 2024-06-25 | 2024-03-09 | 2024-03-19 | 889757 | 2024-03-27 | 2024-07-05 |  |  | 3 phase meter with 25KVA PMT | Closed
53229 | North | N1 | IESCO | Y2024 | New-Self | 2024-11-30 | Highrise | Rawat | Islamabad | Islamabad | Alvi Laboratory, Jawa Road, Rawat, Islamabad | On-Air | 2024-06-05 | 2024-06-28 | 2024-11-15 | 2024-11-18 | 755433 | 2024-11-19 | 2025-03-05 |  |  | 3 phase meter with 25KVA PMT | Closed
53248 | North | N3 | PESCO | Y2024 | New-Self | 2024-08-26 18:52 | S&S | Swabi | Swabi | Swabi | Gharibabad Maniri, Swabi | On-Air | 2024-06-06 | 2024-07-23 | 2024-07-02 | 2024-07-03 | 783,064 | 2024-07-23 | 2024-10-07 |  |  | Permanent Power | Closed
53277 | North | N1 | IESCO | Y2024 | New-Self | 2024-07-30 10:53 | Highrise | Attock | Attock | Attock | Near Aysha Masjid, Peoples Colony, Attock | On-Air | 2024-06-06 | 2024-08-23 | 2024-08-30 | 2024-09-06 | 959487 | 2024-09-19 | 2025-01-07 |  |  | 3 phase meter with 25KVA PMT | Closed
53278 | North | N1 | IESCO | Y2024 | New-Self | 2024-10-31 19:09 | Highrise | Hasan Abdal_Rural | Hassanabdal | Wah+Taxila | Near street no 2, Along nalla, Phase 2 New City, Wah | On-Air | 2024-06-06 | 2024-08-12 | 2024-07-03 | 2024-07-05 | 743,741 | 2024-07-13 | 2024-08-26 |  |  | Permanent Power | Closed
53305 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | Highrise | Rawalpindi_Rural | Rawalpindi | Rawalpindi | Near Chakri Interchange M2,Qurtaba Road, gheela kalan, Rawalpindi | On-Air | 2024-06-06 | 2024-07-12 | 2024-07-16 | 2024-07-19 | 1077251 | 2024-07-30 | 2024-08-20 |  |  | 3 phase meter with 25KVA PMT | Closed
53320 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Rawalpindi | Rawalpindi | Rawalpindi | Street 17, Usman Block Bahria Safari Valley, Rawalpindi | On-Air | 2024-06-06 | 2024-07-23 | 2024-06-26 | 2024-06-26 | 806,709 | 2024-07-24 | 2024-08-18 |  |  | Permanent Power | Closed
53353 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Rawalpindi | Rawalpindi | Rawalpindi | OHWT Bahria Town Intellectual Village, Rawalpindi | On-Air | 2024-06-10 | 2024-07-27 | 2024-09-04 | 2024-09-04 | 961946 | 2024-09-14 | 2024-12-10 |  |  | 3 phase meter with 25KVA PMT | Closed
53379 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-08 | Highrise | Bajna | Bajna | Mansehra | PO Dodhyal Shanai Bala Tehsil & District Mansehra | On-Air | 2024-06-10 | 2024-07-29 |  | 2024-07-01 | 683,228 | 2024-07-18 | 2024-08-16 |  |  | Permanent Power | Closed
53394 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 23:22 | S&S | Manshehra | Manshehra | Manshehra | Ghazikot, PO Manshera, Tehsil & District Manshera | On-Air | 2024-06-10 | [9 empty] | Pending
53405 | North | N2 | PESCO | Y2024 | New-Self | 2024-12-06 | Highrise | Pabbi_Rural | Pabbi | Nowshera | Banda Shekh Ismail Khan Road, Tarkha, Nowshera | On-Air | 2024-06-10 | [9 empty] | Pending
53412 | North | N2 | PESCO | Y2024 | New-Self | 2024-08-31 23:40 | S&S | Kohat_Rural | Kohat | Kohat | Kohat Hangu Road, Chakar Kot, Kohat | On-Air | 2024-06-11 | 2024-10-21 | 2024-07-01 | 2024-07-03 | 723407 | 2024-07-09 | 2024-07-25 |  |  | 3 phase meter with 25KVA PMT | Closed
53453 | North | N3 | PESCO |  | New-Self |  | Highrise | Mardan_Rural | Mardan | Mardan | Garhi Kapura, Mardan | On-Air | 2024-06-11 | [9 empty] | Pending
53540 | North | N2 | PESCO | Y2024 | New-Self | 2024-09-01 00:10 | Highrise | Bara_Rural | Bara | FATA | Main Bazar Koi Chowk Bara, Khyber | On-Air | 2024-06-21 | 2024-07-28 | 2024-07-10 | 2024-07-10 | 1,368,507 | 2024-07-24 | 2024-08-12 |  |  | Permanent Power | Closed
53542 | North | N2 | PESCO |  | New-Self |  | S&S | Peshawer | Peshawer | Peshawer | Warsak Road, PO Garhi Sher dad Garhi Sher dad Tehsil & District Peshawar | On-Air | 2024-06-23 | 2024-07-22 |  | 2024-07-12 | 996,284 | 2024-07-31 | 2024-09-12 |  |  | Permanent Power | Closed
53558 | North | N1 | IESCO | Y2024 | New-Self | 2023-10-19 12:39 | Highrise | 0 | Mansehra | Mansehra | Terha Road, Malik Pur,Bheerkund, Mansehra | On-Air | 2024-06-24 | 2024-07-28 | 2024-07-11 | 2024-07-18 | 77,600 | 2024-07-25 | 2024-08-08 |  |  | Permanent Power | Closed
53578 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Rawalpindi | Rawalpindi | Rawalpindi | Bahria Safari Valley, Rawalpindi | On-Air | 2024-06-25 | 2024-07-27 | 2024-07-09 | 2024-07-11 | 1,493,244 | 2024-07-22 | 2024-08-30 |  |  | Permanent Power | Closed
53579 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Islamabad | Islamabad | Islamabad | Street no 15, Sector I-10/1, Islamabad | On-Air | 2024-06-27 |  | 2025-01-07 | 2025-01-08 | 738,556 | 2025-01-16 | 2025-02-11 |  |  | Permanent Power | Closed
53595 | North | N2 | PESCO | Y2024 | New-Self | 2024-09-30 23:29 | Highrise | Lahor_Rural | Swabi | Swabi | Jalbai, Jehangira | On-Air | 2024-06-27 | 2024-08-05 | 2024-07-15 | 2024-07-24 | 723,166 | 2024-08-07 | 2024-08-24 |  |  | Permanent Power | Closed
53596 | North | N2 | PESCO | Y2024 | New-Self | 2024-09-30 10:30 | S&S | Lahor_Rural | Swabi | Swabi | Manki Tano Road, Manki, Jehangira | CW Kick-off Done | 2024-06-27 | [9 empty] | Pending
53653 | North | N2 | PESCO | Y2024 | New-Self | 2024-04-30 17:01 | S&S | Peshawar | Peshawar | Peshawar | Ring Road Peshawar | On-Air | 2024-06-28 | 2024-08-24 | 2024-07-23 | 2024-08-01 | 1,128,700 | 2024-08-06 | 2024-08-28 |  |  | Permanent Power | Closed
53664 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | Highrise | - | Rawalpindi | Rawalpindi | Dhoke Kala Khan. Rawalpindi. | On-Air | 2024-07-02 | 2024-07-26 | YES | 2024-08-12 | 858,548 | 2024-08-20 | 2024-08-24 |  | 2024-09-21 | Permanent Power | Closed
53686 | North | N4 | IESCO | Y2024 | New-Self | 2024-10-31 19:03 | Highrise | Rawalpindi | Rawalpindi | Rawalpindi | Near Main IJP Road, Dhok Hassu, Rawalpindi | On-Air | 2024-07-11 | [9 empty] | Pending
53698 | North | N2 | PESCO | Y2024 | New-Self | 2024-09-30 10:30 | Highrise | - | Peshawar | Peshawar | Darmangi Bazar, Warsak Road, Peshawar. | On-Air | 2024-07-15 | 2024-08-28 | 2024-08-09 | 2024-08-09 | 734,241 | 2024-08-28 | 2024-09-27 |  |  | Permanent Power | Closed
53707 | North | N3 | PESCO | Y2024 | New-Self | 2024-06-30 | S&S | - | Mardan | Mardan | Nazar Bostan BaBa colony Tehsil and District Mardan | On-Air | 2024-07-15 | 2024-08-19 | 2024-07-23 | 2024-08-01 | 761,500 | 2024-09-23 | 2024-09-17 |  |  | Permanent Power | Closed
53734 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | Highrise | - | Attock | Attock | Ghulam Jilani, Bark Road, Attock. | Integrated | 2024-07-15 | [9 empty] | Pending
53752 | North | N3 | PESCO | Y2024 | New-Self | 2024-07-31 16:58 | Highrise | Mardan | Mardan | Mardan | Khawaja Ganj Bazar near Kalpani Pull Hoti Bazar Mardan | On-Air | 2024-07-22 | 2024-08-27 |  | 2024-08-09 | 1536892 | 2024-08-26 | 2024-11-23 |  |  | 3 phase meter with 25KVA PMT | Closed
53755 | North | N3 | PESCO |  | COW | 2023-11-30 | COW | #N/A | #N/A | #N/A | #N/A | On-Air | 2024-07-22 | 2024-08-22 |  | 2024-08-09 | 1513899 | 2024-08-28 | 2024-11-10 |  |  | 3 phase meter with 25KVA PMT | Closed
53759 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | S&S | Islamabad | Islamabad | Islamabad | G-8 Islamabad | On-Air | 2024-07-25 | 2024-10-22 |  | 2024-10-01 | 2,018,864 | 2024-10-18 | 2024-12-27 |  |  | Permanent Power | Closed
53760 | North | N2 | PESCO | Y2024 | New-Self | 2024-06-30 | S&S | Jahangira | 0 | Swabi | Mouza Garho Khasra NO 1239 Nizam Pur Tehsil Jahangira Dist Nowshera | On-Air | 2024-07-25 | 2024-09-04 |  | 2024-10-01 | 2,177,350 | 2024-10-18 | 2024-12-05 |  |  | Permanent Power | Closed
53761 | North | N2 | PESCO | Y2024 | New-Self | 2024-05-21 | S&S | Lucky Marwat | Lucky Marwat | Lucky Marwat | Lucky cement factory Pezu Plant, Pezu Lakki Marwat, KPK | RFI without Power | 2024-07-25 |  |  | 2024-10-07 | 2,137,725 | 2024-10-18 | 2025-03-02 |  | PCP | 3 phase meter with 25KVA PMT | Closed
53762 | North | N3 | PESCO |  | New-Self | 2024-12-23 18:01 | Highrise | Rawalkot | Rawalkot | AJK | Hotel Pearl International, PWD Rd, Tehsil Rawalakot, District Poonch, AJK | On-Air | 2024-07-26 | 2024-08-22 |  | 2024-08-29 | 1882437 | 2024-09-09 | 2025-02-25 |  |  | 3 phase meter with 25KVA PMT | Closed
53770 | North | N1 | IESCO | Y2024 | New-Self | 2024-06-30 | Highrise | Bhara Kahu | Islamabad | Islamabad | Sherzaman Janjua, Bara Kahu P/O Khas Tehsil & District Islamabad | On-Air | 2024-07-26 | 2024-08-27 |  | 2024-09-26 | 2233813 | 2024-10-07 | 2025-02-16 |  |  | 3 phase meter with 25KVA PMT | Closed
53772 | North | N1 | IESCO | Y2024 | New-Self | 2024-08-31 23:45 | Highrise | Islamabad | Islamabad | Islamabad | Alipur Farash Town, Lehtrar Road, Islamabad. | On-Air | 2024-07-26 | 2024-08-30 |  | 2024-08-29 | 1882437 | 2024-09-09 | 2025-01-07 |  |  | 3 phase meter with 25KVA PMT | Closed
53781 | North | N1 | IESCO | Y2024 | New-Self | 2024-09-23 11:22 | Highrise | Attock_Rural | Attock | Attock | Phase 3, water tank, Mehria Town Attock. | On-Air | 2024-07-26 | 2024-11-20 |  |  | 1,172,869 | [5 empty] | Pending
53783 | North | N2 | PESCO | Y2024 | New-Self | 2024-10-31 22:13 | Highrise | Peshawar Pda Hyatabad | Peshawar | Peshawar | Phase B Hayatabad Peshawer | On-Air | 2024-07-26 | 2024-08-23 |  | 2024-08-29 | 169206 | 2024-09-09 | 2024-11-10 |  |  | 3 phase meter with 25KVA PMT | Closed
53800 | North | N2 | PESCO |  | New-Self |  | S&S | Jehangira_Rural | Jehangira | Nowshera | Mohallah Noor Khan gari, Shaidu, District Nowshehra. | On-Air | 2024-07-26 | 2024-08-28 | YES | YES | 964,739 | 2024-08-22 | 2024-11-04 |  |  | Permanent Power | Closed
53803 | North | N2 | PESCO | Y2024 | New-Self | 2024-07-31 10:28 | Highrise | Peshawar | Peshawar | Peshawar | Mohallah Nazar abad Shaheen Muslim Town Peshawar | On-Air | 2024-07-26 | 2024-09-07 |  | 2024-08-22 | 767454 | 2024-09-02 | 2024-10-18 |  |  | 3 phase meter with 25KVA PMT | Closed
53805 | North | N1 | IESCO | Y2024 | New-Self | 2024-05-31 | Highrise | Rawalpindi | Rawalpindi | Rawalpindi | PO Pindory, Thala khurd, Tehsil and District Rawalpindi | On-Air | 2024-07-26 | [5 empty] | Off Grid | Off Grid | Off Grid | Off Grid | Off Grid
53809 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 10:28 | S&S | - | Mardan | Mardan | Bukhshli Interchange Toll Plaza Mardan | On-Air | 2024-07-29 | 2024-12-24 |  | 2024-09-19 | 732683 | 2024-12-19 | 2025-02-26 | TCP |  | TCP | Closed
53811 | North | N1 | IESCO | Y2024 | New-Self | 2024-07-30 17:14 | Highrise | Islamabad | Islamabad | Islamabad | Naval Anchorage , Islamabad | On-Air | 2024-07-29 | 2024-09-20 | 2024-09-09 | 2024-09-12 | 743517 | 2024-09-23 | 2025-01-07 |  |  | 3 phase meter with 25KVA PMT | Closed
53813 | North | N1 | IESCO |  | New-Self |  | S&S | Rawalpindi | Rawalpindi | Rawalpindi | Qasim Abad, Street NO. 11, Rawalpindi Cantt | On-Air | 2024-07-30 | 2024-10-14 | 2024-10-07 | 2024-10-10 | 1,067,382 | 2024-10-30 | 2024-12-05 |  |  | Permanent Power | Closed
53815 | North | N2 | PESCO |  | New-Self | 2024-09-01 00:29 | S&S | Peshawar | Peshawar | Peshawar | Canal Town Peshawar, | On-Air | 2024-07-30 | 2024-09-04 | 2024-08-15 | 2024-08-13 | 652,122 | 2024-08-20 | 2024-12-02 |  |  | Permanent Power | Closed
53827 | North | N2 | PESCO | Y2024 | New-Self | 2024-06-30 | Highrise | Peshawar | Peshawar | Peshawar | Almas Car Village Ring Road Peshawar | On-Air | 2024-07-30 | 2024-09-19 | YES | 2024-08-06 | 967,395 | 2024-08-22 | 2024-09-27 |  |  | Permanent Power | Closed
53829 | North | N1 | IESCO |  | New-Self |  | S&S | Islamabad | Islamabad | Islamabad | Eighteen Society, Srinagar Highway, Islamabad | On-Air | 2024-07-30 | [9 empty] | Pending
53832 | North | N2 | PESCO | Y2024 | New-Self | 2024-10-31 19:08 | Highrise | Kohat-Hangu | HANGU | Kohat-Hangu | Village Tahati Banda Tehsil & District Hango | On-Air | 2024-07-31 | 2024-09-02 |  | 2024-09-26 | 1538982 | 2024-10-07 | 2024-12-19 |  |  | 3 phase meter with 25KVA PMT | Closed
53833 | North | N2 | PESCO | Y2024 | New-Self | 2024-08-31 21:05 | Highrise | Kohat-Hangu | HANGU | Kohat-Hangu | PO PTC, Mardo Khel Tehsil & District Hangu | On-Air | 2024-07-31 | 2024-08-29 | 2024-09-09 | 2024-09-12 | 1291401 | 2024-09-23 | 2025-02-13 |  |  | 3 phase meter with 25KVA PMT | Closed
53843 | North | N2 | PESCO | Y2024 | New-Self | 2024-07-31 20:24 | Highrise | Kohat-Hangu | KOHAT | Kohat-Hangu | Village Ghulam Banda, Kohat | On-Air | 2024-08-01 | 2024-10-25 | 2024-09-30 | 2024-10-03 | 964,838 | 2024-10-25 | 2024-12-07 |  |  | Permanent Power | Closed
53846 | North | N2 | PESCO | Y2024 | New-Self | 2024-09-30 10:28 | Highrise | Kohat-Hangu | KOHAT | Kohat-Hangu | Masjid Bilal , Qabail Coloney, PO Kohat Jarma, Tehsil & District Kohat | On-Air | 2024-08-02 | 2024-09-06 |  | 2024-09-04 | 962,906 | 2024-09-19 | 2024-11-20 |  |  | Permanent Power | Closed
53847 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-29 11:45 | Highrise | Swat | SWAT | Swat | Haqla Sar, Village behar adwo Tehsil Khawazkhela District Swat | On-Air | 2024-08-05 | 2024-11-28 |  | 2024-10-17 | 2,470,885 | 2024-11-18 | 2025-02-08 |  |  | Permanent Power | Closed
53851 | North | N3 | PESCO | Y2024 | New-Self | 2024-07-30 16:48 | Highrise | Swat | SWAT | Swat | Mohallah Dolat Khel, Takhta Band PO Angro Dherai, Tehsil & District Swat. | On-Air | 2024-08-05 | 2024-10-06 |  | 2024-10-17 | 2,258,355 | 2024-10-30 | 2024-12-05 |  |  | Permanent Power | Closed
53858 | North | N3 | PESCO | Y2024 | New-Self | 2024-06-30 | Highrise | Swat | SWAT | Swat | Langar PO Khawazakhela, Tehsil Khawazakhela District Swat. | On-Air | 2024-08-05 | 2024-10-06 |  | 2024-09-04 | 1,977,799 | 2024-09-23 | 2024-11-04 |  |  | Permanent Power | Closed
53859 | North | N3 | PESCO |  | New-Self |  | Highrise | Swat | SWAT | Swat | Bar Kalay Khawaza Khela District Swat | On-Air | 2024-08-05 | 2024-08-29 | 2024-08-16 | 2024-09-05 | 70,650 | 2024-09-05 | 2024-09-14 |  |  | Permanent Power | Closed
53860 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 16:14 | Highrise | Swat | SWAT | Swat | Shalpeen, Swat. | RFI without Power | 2024-08-06 | [9 empty] | Pending
53861 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 19:07 | Highrise | Swat | SWAT | Swat | PO Khawaz Khela, Chankolai, Tehsil Khawaz Khela, District Swat. | On-Air | 2024-08-06 | 2024-09-18 | Yes | 2024-08-19 | 923,882 | 2024-09-03 | 2024-09-26 |  |  | Permanent Power | Closed
53863 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 17:22 | Highrise | Swat | SWAT | Swat | Shagai Shahgram aryana, PO Madyan, Tehsil Bahrain District Swat | Integrated | 2024-08-09 | [5 empty] | Off Grid | Off Grid | Off Grid | Off Grid | Off Grid
53864 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 18:25 | Highrise | Swat | SWAT | Swat | Shainko, PO Madyan, Tehsil Bahrain District Swat | On-Air | 2024-08-12 | 2024-09-18 | 2024-09-26 | 2024-10-04 | 33500 | 2024-10-08 | 2025-01-01 |  |  | TCP | Closed
53865 | North | N3 | PESCO |  | New-Self |  | Highrise | Swat | SWAT | Swat | Bahrain Kamblay District Swat | On-Air | 2024-08-12 |  | 2024-08-16 | 2024-09-03 | 652,149 | 2024-09-18 | 2024-10-17 |  |  | Permanent Power | Closed
53866 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-26 18:30 | Highrise | Swat | SWAT | Swat | Torwal Kon Tatt Tehsil Bahrain District Swat | On-Air | 2024-08-12 | 2024-09-20 |  | 2024-09-11 | 901967 | 2024-09-18 | 2024-12-03 |  | PCP | 3 phase meter with 25KVA PMT | Closed
53870 | North | N3 | PESCO | Y2024 | New-Self | 2024-08-31 23:44 | Highrise | Swat | SWAT | Swat | Mona Golistan Viallage Koza Banda Tehsil Kabal District Swat | On-Air | 2024-08-13 | 2024-09-22 | 2024-10-01 | 2024-10-08 | 1745427 | 2024-10-24 | 2024-11-23 |  |  | 3 phase meter with 25KVA PMT | Closed
53871 | North | N3 | PESCO | Y2024 | New-Self | 2024-07-31 16:57 | Highrise | Swat | SWAT | Swat | Mohallah Nikar Abad Koza Banda | On-Air | 2024-08-13 | 2024-10-07 | 2024-09-19 | 2024-09-20 | 835853 | 2024-09-23 | 2025-01-07 |  |  | 3 phase meter with 25KVA PMT | Closed
53872 | North | N3 | PESCO |  | New-Self |  | Highrise | Swat | SWAT | Swat | Mohallah Shakardara PO Bar Sher Palam Shakardara Tehsil Matta District Swat | RFI without Power | 2024-08-13 |  | 2025-01-07 | 2025-01-13 | 1,111,205 | [5 empty] | Pending | 2025-04-25
53873 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-29 23:17 | Highrise | Swat | SWAT | Swat | PO Matta, Pir Kalay Tehsil Matta, District Swat. | On-Air | 2024-08-15 | [5 empty] | Off Grid | Off Grid | Off Grid | Off Grid | Off Grid
53876 | North | N3 | PESCO |  | New-Self |  | Highrise | Swat | SWAT | Swat | Koz Paloo Baidara Tehsil Matta District Swat | On-Air | 2024-08-16 | 2024-09-27 | 2024-10-07 |  | 1,147,930 | 2024-10-29 | 2024-12-15 |  |  | Permanent Power | Closed
53882 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 18:04 | Highrise | Swat | SWAT | Swat | PO Rorringar, Rorringara Gawaleerai, Tehsil Matta, District Swat. | CW Kick-off Done | 2024-08-16 | [9 empty] | Pending
53886 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-23 17:58 | Highrise | Swat | SWAT | Swat | Barplo, PO Garhi, Shamozai (Ghari) Tehsil Barikot District Swat | On-Air | 2024-08-16 | [5 empty] | Off Grid | Off Grid | Off Grid | Off Grid | Off Grid
53890 | North | N2 | PESCO |  | New-Self | 2024-12-23 12:37 | S&S | 0 | 0 | Peshawar | Village Kaga Wala Touheedabad Kohat Road Badebere Peshawar | On-Air | 2024-08-16 | 2024-09-28 |  |  |  |  | Off Grid | Off Grid | Off Grid | Off Grid | Off Grid
53891 | North | N1 | IESCO | Y2024 | New-Self | 2024-04-30 | S&S | Rawalpindi | Rawalpindi | Rawalpindi | Attock House, Morgah Road, Rawalpindi | On-Air | 2024-08-16 | [9 empty] | Pending
53897 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-27 17:12 | S&S | Buner | Buner | Buner | Kankowai Tehsil Mandarh District Buner | On-Air | 2024-08-22 | [9 empty] | Pending
53900 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 23:52 | S&S | Buner | Buner | Buner | Hisar Daggar District Buner | On-Air | 2024-08-23 | 2024-09-27 | 2024-11-07 | 2024-11-14 | 1122381 | 2024-12-10 | CP will be installed on 5 Mar 25 | CP will be installed on 5 Mar 25 | CP will be installed on 5 Mar 25 | CP will be installed on 5 Mar 25
53901 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 20:18 | S&S | Buner | Buner | Buner | PO Daggar, Topadrah, Tehsil Daggar District Buner | On-Air | 2024-08-23 | 2024-10-24 | 2024-10-08 | 2024-10-14 | 857,162 | 2024-10-31 | 2024-12-06 |  |  | Permanent Power | Closed
53902 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 22:08 | S&S | Buner | Buner | Buner | PO Dagar Tehsil Diggar District Buner | On-Air | 2024-08-28 | 2024-08-29 | 2024-08-23 | 2024-08-26 | 659,884 | 2024-08-29 | 2024-09-10 |  |  | Permanent Power | Closed
53903 | North | N3 | PESCO |  | New-Self |  | Highrise | Buner | Buner | Buner | Muhallah Patao Bazarge PO Bazarge Tehsil Daggar, District Bunir | On-Air | 2024-09-03 | 2024-09-28 | 2024-10-14 | 2024-10-15 | 981443 | 2024-10-21 | 2025-01-10 |  | PCP | 3 phase meter with 25KVA PMT | Closed
53904 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-06 | Highrise | Buner | Buner | Buner | Mohallah Patao, PO Jorr Chowk, Dagar District Buner | On-Air | 2024-09-04 | [9 empty] | Pending
53905 | North | N3 | PESCO |  | New-Self |  | Highrise | Buner | Buner | Buner | Gadizai Tor Tangi Nansaid Tehsil Daggar District Buner | On-Air | 2024-09-05 | 2024-10-12 |  | 2024-10-17 | 1,737,379 | 2024-10-30 | 2024-12-04 |  |  | Permanent Power | Closed
53908 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-31 14:13 | Highrise | Buner | Buner | Buner | PO Khana Badal. Bodal, Tehsil Gagrah District Buner | On-Air | 2024-09-05 | 2024-10-14 | [8 empty] | Pending
53909 | North | N3 | PESCO |  | New-Self |  | Highrise | Buner | Buner | Buner | Garhi Hujro Batara Tehsil Gagra District Buner | On-Air | 2024-09-05 | 2024-10-14 | [8 empty] | Pending
53910 | North | N3 | PESCO |  | New-Self |  | Highrise | Buner | Buner | Buner | PO Gulabandi Tangora Tehsil Gagra District Buner Pakistan | On-Air | 2024-09-05 | [9 empty] | Pending
53912 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-29 23:19 | Highrise | Buner | Buner | Buner | Jaffar Khel, Changlai, Tehsil Khado Khel District Buner | On-Air | 2024-09-10 | 2024-10-22 | [8 empty] | Pending
53921 | North | N3 | PESCO |  | New-Self |  | S&S | Gilgit | Gilgit | Gilgit | Farfoh Pati, PO Khass, Oshikhandass, Tehsil & District Gilgit | On-Air | 2024-09-12 | 2024-10-29 | 2024-10-29 | 2024-10-29 | 842666 | 2024-11-06 | 2025-02-22 |  |  | Permanent Power | Closed
53923 | North | N2 | PESCO | Y2024 | New-Self | 2024-11-27 11:33 | Highrise | Karak | Karak | Karak | Makori, Tehsil Banda Dawood Shah District Karak | On-Air | 2024-09-12 | 2024-10-22 | 2024-10-14 | 2024-10-29 | 833,288 | 2024-11-06 | 2024-12-28 |  |  | Permanent Power | Closed
53924 | North | N1 | IESCO | Y2024 | New-Self | 2024-10-15 | Highrise | Islamabad | Islamabad | Islamabad | Allied Bank Near Airport Top City Islamabad | On-Air | 2024-09-12 | 2024-10-22 | Yes | 2024-10-21 | 786,021 | 2024-10-29 | 2024-11-27 | 2024-11-27 |  | Advance Meter | Closed
53927 | North | N1 | IESCO | Y2024 | New-Self | 2024-10-31 23:34 | Highrise | Islamabad | Islamabad | Islamabad | AD Hieghts Al-Razzaq Valley Near Pindoriyan Islamabad | On-Air | 2024-09-12 | 2024-10-23 | Yes | 2024-10-21 | 681,694 | 2024-10-29 | 2024-11-27 |  | 2025-02-14 | Advance Meter | Closed
53929 | North | N1 | IESCO | Y2024 | New-Self | 2024-08-31 21:07 | Highrise | Rawalpindi | Rawalpindi | Rawalpindi | Old Shakrial Mohallah Sadat PO Khas, Tehsil & District Rawalpindi | On-Air | 2024-09-12 | [5 empty] | Off Grid |  |  | Off-Grid | Off Grid
53934 | North | N2 | PESCO | Y2024 | New-Self | 2024-08-31 23:44 | Highrise | Nowshehra | Nowshehra | Nowshehra | Barra, Gharra, Akbar Pora Tehsil Pabbi, District Nowshera | On-Air | 2024-09-13 | 2024-09-29 | 2024-10-07 | 2024-10-09 | 742,632 | 2024-10-11 | 2024-11-02 |  |  | Permanent Power | Closed
53940 | North | N1 | IESCO | Y2024 | New-Self | 2024-09-01 00:25 | Highrise | Islamabad | Islamabad | Islamabad | DHAI Teleman Sector C DHA Phase 5, Islamabad | On-Air | 2024-09-16 | 2024-10-14 | 2024-09-25 | 2024-09-25 | 91,880 | 2024-09-27 | 2024-10-10 |  |  | Permanent Power | Closed
53941 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 19:38 | Highrise | Bajaur | Bajaur | Bajaur | Gardai, Tehsil Utman Khel District Bajaur | On-Air | 2024-09-18 | 2024-10-23 |  | 2024-11-11 | 916,006 | 2025-01-02 |  |  |  |  | Pending
53943 | North | N3 | TESCO | Y2024 | New-Self | 2024-08-31 23:43 | S&S | Bajaur | Bajaur | Bajaur | PO Khar, Haji lawang Tehsil khar Bajaur District Bajaur | On-Air | 2024-09-25 | 2024-10-27 | YES | 2024-10-24 | 555,766 | 2024-11-11 | 2025-02-22 |  |  | Permanent Power | Closed
53944 | North | N3 | TESCO |  | New-Self |  | Highrise | Bajaur | Bajaur | Bajaur | Khohi Sar, PO Kher,Tehsil Barang District Bajaur Agency | On-Air | 2024-09-25 | 2024-10-26 | [8 empty] | Pending
53946 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 22:06 | Highrise | Bajaur | Bajaur | Bajaur | Charmang, Tangay Khar, Tehsil Khar Bajaur District Bajuar | On-Air | 2024-09-26 | 2024-10-28 | 2024-11-12 | 2024-11-12 | 899,340 | 2024-11-19 |  |  |  |  | Pending
53947 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-27 17:12 | Highrise | Bajaur | Bajaur | Bajaur | Charmang, PO Loei Sam Syeda Shah Tehsil Nawagai District Bajuar Agency | On-Air | 2024-09-27 | [9 empty] | Pending
53948 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | Bajaur | Bajaur | Bajaur | Loi Sum, Tehsil Khar Bajaur District Bajuar Agency | On-Air | 2024-10-02 | 2024-10-10 | 2024-10-09 | 2024-10-10 | 2,569,542 | 2024-10-11 | 2024-10-11 |  |  | Permanent Power | Closed
53949 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 20:15 | S&S | Bajaur | Bajaur | Bajaur | PO Khar, Markhanai Tehsil Salarzai Bajaur Agency | On-Air | 2024-10-03 | 2024-11-05 | 2024-10-29 | 2024-10-29 | 733379 | 2024-11-05 | 2025-02-21 |  |  | Permanent Power | Closed
53951 | North | N3 | PESCO | Y2024 | New-Self | 2024-08-31 22:39 | S&S | Bajaur | Bajaur | Bajaur | PO Khana Khar, Balolai, Tehsil Khar Bajaur District Bajaur | On-Air | 2024-10-08 | 2024-11-28 | 2024-11-21 | 2024-11-21 | 1,843,448 | 2024-12-04 | 2025-01-06 |  |  | Permanent Power | Closed
53952 | North | N3 | PESCO | Y2024 | New-Self | 2024-08-31 22:43 | S&S | Bajaur | Bajaur | Bajaur | Shandy Morh,Tehsil Khar, District Bajaur | On-Air | 2024-10-08 | 2024-10-23 | 2024-10-31 | 2024-10-31 | 732,789 | 2024-11-08 | 2025-01-01 |  |  | Permanent Power | Closed
53953 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 10:28 | S&S | Bajaur | Bajaur | Bajaur | PO Anayat Kalay, Inam kharo changyi Tehsil Mamund, District Bajaur | On-Air | 2024-10-08 | [9 empty] | Pending
53954 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 19:17 | Highrise | Bajaur | Bajaur | Bajaur | Tangy PO Anayat Kalay Tehsil Momand District Bajaur Agency | On-Air | 2024-10-10 | 2024-12-22 | [8 empty] | Pending
53956 | North | N3 | TESCO | Y2024 | New-Self | 2024-09-30 20:10 | S&S | Bajaur | Bajaur | Bajaur | Govt. primary scholl biloat PO Inayat Kallay Badan Tehsil Mamund, District Bajaur | On-Air | 2024-10-10 | 2024-10-24 | 2024-11-12 | 2024-11-14 | 277,400 | 2024-11-15 | 2024-11-19 | 2024-11-19 |  | Official Temporary Power | Closed
53957 | North | N3 | PESCO |  | New-Self |  | Highrise | Bajaur | Bajaur | Bajaur | PO Anayat Kalay Bedan Tehsil Momand District Bajuar Agency | On-Air | 2024-10-10 | [9 empty] | Pending
53958 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 18:02 | S&S | Bajaur | Bajaur | Bajaur | PO Inayat Kallay Bara Amanata Tehsil Mamund District Bajaur Agency | On-Air | 2024-10-11 | [9 empty] | Pending
53960 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 18:25 | Highrise | Bajaur | Bajaur | Bajaur | Rehman Abad, PO Anayat Kalay, Nawa kalay, Tehsil Khar Bajuar District Bajuar | On-Air | 2024-10-14 |  |  | 2024-12-09 | 677,500 |  | 2025-01-05 |  |  | Permanent Power | Closed
53962 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 19:05 | S&S | Bajaur | Bajaur | Bajaur | PO Raghgan Tallay Tehsil Salarzai District Bajaur | On-Air | 2024-10-15 | 2024-11-12 | 2024-11-06 | 2024-11-09 | 1,237,242 | 2024-11-15 |  |  |  |  | Pending
53963 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 19:04 | Highrise | Bajaur | Bajaur | Bajaur | PO Ragagan, Gidershy, Tehsil Salarazy District Bajaur | On-Air | 2024-10-17 | 2024-11-17 | 2024-11-12 | 2024-11-04 | 1,015,038 | 2024-11-19 | 2024-12-07 |  | 2025-02-06 | Permanent Power | Closed
53964 | North | N3 | TESCO | Y2024 | New-Self | 2024-11-30 | Highrise | Bajaur | Bajaur | Bajaur | Shah Toot PO Raggan Balam Khar Tehsil Salarzai District Bajaur | On-Air | 2024-10-24 | 2024-11-28 |  | 2024-11-27 | 1,753,221 |  | 2025-01-26 |  |  | Permanent Power | Closed
53965 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-06 | Highrise | Bajaur | Bajaur | Bajaur | PO Pashat Batmalai Tehsil Salarzai District Bajaur | On-Air | 2024-10-24 | 2024-12-25 | 2024-12-15 | 2024-12-19 | 868,854 |  | 2025-03-09 |  | PCP | 3 Phase PCP with 25 Kva TF | Closed
53966 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 10:30 | Highrise | Bajaur | Bajaur | Bajaur | Kohi Shah PO Qazafi, Banda Gai, Tehsil Itman Khel, District Bajuar Agency | On-Air | 2024-10-24 | 2024-11-29 |  | 2024-11-27 | 2,000,839 |  | 2024-12-27 |  |  | Permanent Power | Closed
53967 | North | N3 | PESCO |  | New-Self |  | Highrise | Bajaur | Bajaur | Bajaur | Nawagai PO Nawagai Tehsil Nawagai District Bajaur Agency | On-Air | 2024-10-25 | 2024-11-29 | 2024-12-06 | 2024-12-11 | 1,069,947 | 2025-01-04 |  |  |  |  | Pending
53969 | North | N3 | TESCO | Y2024 | New-Self | 2024-11-30 | Highrise | Bajaur | Bajaur | Bajaur | PO Raghgan Tiya Tehsil Salarazy District Bajaur | On-Air | 2024-11-01 | 2024-12-16 |  | 2024-12-24 | 1,398,577 | 2025-01-22 |  |  |  |  | Pending
53972 | North | N3 | PESCO |  | New-Self |  | Highrise | Bajaur | Bajaur | Bajaur | Arang, PO Groai, Pajigram, Tehsil Itman Khel District Bajaur | On-Air | 2024-11-06 | 2024-12-03 | [8 empty] | Pending
53973 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | Bajaur | Bajaur | Bajaur | Narazay PO Raghgan Tehsil Salarzai District Bajaur Agency | On-Air | 2024-11-18 | 2024-12-01 | YES | YES | 665,134 | 2024-12-04 | 2025-02-21 |  |  | Permanent Power | Closed
53974 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 20:16 | Highrise | Bajaur | Bajaur | Bajaur | PO Pushat Tarano Tehsil Salarazy District Bajaur | On-Air | 2024-11-18 |  |  | 2025-01-17 | 824,881 | [5 empty] | Pending
53975 | North | N3 | PESCO |  | New-Self |  | Highrise | Bajaur | Bajaur | Bajaur | PO Khar, Tangai, Tehsil Salarzai District Bajaur | On-Air | 2024-11-19 | [9 empty] | Pending
53978 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 19:39 | Highrise | Dir_Rural | Upper Dir | Upper Dir | Muhallah Royan Payyan PO Dir, dir Town Tehsil Dir, District Upper Dir | On-Air | 2024-11-22 | [9 empty] | Pending
53979 | North | N2 | PESCO |  | New-Self | 2024-12-31 | Highrise | Peshawar | Peshawar | Peshawar | NEAR ZONE 3 GOUND WATER TANK REGI Peshawar | On-Air | 2024-12-03 | 2024-12-26 | 2024-10-09 | 2024-10-10 | 1,187,605 | 2024-10-11 | 2024-10-12 |  |  | Permanent Power | Closed
53984 | North | N1 | IESCO |  | New-Self | 2024-12-18 14:50 | Highrise | Kotli Sattian | Kotli Sattian | Rawalpindi | Sangri Sangriyan, PO Kahoti Bazar, Tehsil Kotli Sattiyan District Rawalpindi | On-Air | 2024-12-03 |  |  |  | MES Case - DN not applicable |  | 2024-12-19 |  |  | Permanent Power | Closed
53986 | North | N1 | IESCO | Y2024 | New-Self | 2024-11-30 | Highrise | Attock | Attock | Attock | Mohallah Syed Qaim Shah, PO Khas Mirza, Tehsil & District Attock | On-Air | 2024-12-19 | [9 empty] | Pending
53989 | North | N2 | PESCO | Y2024 | New-Self | 2024-09-30 23:06 | S&S | Lakki Marwat | Lakki Marwat | Lakki Marwat | Mohalla Haqdad Abad, Mena Khail, Lakki Marwat | On-Air | 2025-01-03 16:49 | [5 empty] | COW Site | COW Site | COW Site | COW Site | Closed
53991 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 18:04 | Highrise | LOWER DIR | LOWER DIR | DIR | PO Kumber, Barkhanai, Tehsil Lalqila, District Lower Dir | On-Air | 2025-01-17 | 2025-01-17 | [8 empty] | Pending
53992 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | Joni Kaly PO Mayar Tehsil Sammar Bagh District Lower Dir | On-Air | COW | COW | [8 empty] | Pending
53993 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | LOWER DIR | LOWER DIR | DIR | PO Khazana, Saloband, Tehsil Sammar Bagh District Lower Dir | CW Kick-off Done | [10 empty] | Pending
53994 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | PO Aspanr Naway Kali, Tehsil Adanzai, District Lower Dir | Excavation In Progress | [10 empty] | Pending
53995 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-29 23:16 | Highrise | LOWER DIR | LOWER DIR | DIR | Mani Band, Temargara, Timergara, District Lower Dir Pakistan | Foundation Completed | [10 empty] | Pending
53996 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | Shpano Kasay PO Samarbagh Tehsil Jandol, District Lower Dir | Excavation In Progress | [10 empty] | Pending
53997 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | Shangai, Totano Bandai Tehsil Kabal District Swat | Foundation Completed |  |  | 2025-01-17 | 2025-01-22 | 653,774 | [5 empty] | Pending | 2025-04-15
53998 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 22:12 | Highrise | LOWER DIR | LOWER DIR | DIR | Mohallah Ahmad Gulai, Dhrai, PO Ziarat Talash, Tehsil Timargira District Lower Dir | CW Kick-off Done | [7 empty] | 2025-04-02 | 2025-04-02 | 2025-04-02 | Pending
53999 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 23:57 | Highrise | LOWER DIR | LOWER DIR | DIR | PO Aooch, Aooch Sharqi Tehsil Udan Zai District Lower Dir | CW Kick-off Done | [10 empty] | Pending
54000 | North | N3 | PESCO |  | New-Self |  | Highrise | UPPER DIR | UPPER DIR | DIR | Bagh No. 1, PO Warri, Tehsil Warri District Uppar Dir | Excavation In Progress | [10 empty] | Pending
54001 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 20:07 | Highrise | UPPER DIR | UPPER DIR | DIR | PO Darwarra, Sarah Shah, Tehsil Dir District Uppar Dir | Excavation In Progress | [10 empty] | Pending
54002 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | LOWER DIR | LOWER DIR | DIR | Barghandho PO Kumbarh Tehsil Lal Qillah Lower Dir | Excavation In Progress | [10 empty] | Pending
54003 | North | N3 | PESCO |  | New-Self |  | Highrise | UPPER DIR | UPPER DIR | DIR | Bebyor Tehsil Dir District Upper Dir | Foundation In Progress | [9 empty] | Off-Grid | Pending
54004 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-08 | Highrise | LOWER DIR | LOWER DIR | DIR | Kory Naoty PO Khal Timergara Lower Dir | Foundation Completed | [10 empty] | Pending | 2025-04-15
54005 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 23:36 | S&S | LOWER DIR | LOWER DIR | DIR | Mohalla Sairai Bala PO Taza Gram Shah Alam Baba Tehsil Adenzai District Lower Dir | Excavation In Progress | [10 empty] | Pending
54008 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-06 | S&S | LOWER DIR | LOWER DIR | DIR | Kodigram Tehsil Adenzai District Lower Dir | RFI without Power | [10 empty] | Pending
54009 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | PO Serai Payan Tehsil Timergara District Lower Dir | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54010 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 23:59 | S&S | LOWER DIR | LOWER DIR | DIR | Bajarho, PO Ziyarat TalashTehsil Timergara District Lower Dir | Foundation Completed |  |  | 2025-01-17 | 2025-02-06 | 972,032 | [5 empty] | Pending | 2025-04-15
54011 | North | N3 | PESCO |  | New-Self |  | Highrise | UPPER DIR | UPPER DIR | DIR | Mohallah Barcham PO Kam Ser Jabbar Tehsil Dir District Upper Dir | Excavation In Progress | [10 empty] | Pending
54012 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | UPPER DIR | UPPER DIR | DIR | PO Dir Alla Tehsil Dir District Upper Dir | Excavation In Progress | [10 empty] | Pending
54013 | North | N3 | PESCO | Y2024 | New-Self | 2024-09-30 17:34 | S&S | LOWER DIR | LOWER DIR | DIR | PO Mayar, Joni Kalay, Tehsil Samar Bagh, District Lower Dir | CW Kick-off Done | [10 empty] | Pending
54014 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 19:16 | Highrise | LOWER DIR | LOWER DIR | DIR | Village Kampati PO Kambarh Lal Killa District Lower Dir | Foundation Completed | [10 empty] | Pending
54015 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-06 | Highrise | LOWER DIR | LOWER DIR | DIR | Maidan Bandai Lal Qila District Lower Dir | CW Kick-off Done | [10 empty] | Pending
54016 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | Dheri PO Rabaat Dhab Tehsil Temergara District Lower Dir | CW Kick-off Done | [6 empty] | TSS Peending | TSS Peending | TSS Peending | TSS Peending
54018 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | LOWER DIR | LOWER DIR | DIR | Jamia Colony, PO Sammar BaghTehsil Samar Bagh, District Lower Dir. | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54020 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | PO Munda Sanzao Tehsil Samar Bagh District Lower Dir | CW Kick-off Done |  |  | 2025-01-23 | 2025-01-23 | 870,918 |  | 2025-02-07 |  | PCP |  | Closed | 2025-03-12
54024 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | PO Samarbagh, Nawa Koto, Samarbagh, District Lower Dir Pakistan | CW Kick-off Done |  |  |  | 2025-02-21 | 673264 | In payment |  |  |  |  | Pending | 2025-03-25
54025 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 23:38 | Highrise | LOWER DIR | LOWER DIR | DIR | Muhallah Kharkani Ouch Gharbi PO Ouch Tehsil Adan Zai District Lower Dir | Foundation In Progress |  |  |  | DN issuance in process | [6 empty] | Pending | 2025-04-25
54028 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-06 | Highrise | LOWER DIR | LOWER DIR | DIR | PO Monda Ghanam Shah Tehsil Samar Bagh District Lower Dir | Foundation In Progress |  |  |  | DN issuance in process | [6 empty] | Pending | 2025-03-20
54030 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 22:44 | Highrise | LOWER DIR | LOWER DIR | DIR | PO Sammar Bagh, Kashodal, Sarala Top Tehsil Samar Bagh, District Lower Dir. | Foundation Completed |  |  | 2025-01-13 | 2025-01-21 | 1,051,225 | [5 empty] | Pending | 2025-04-25
54031 |  | N3 |  |  | Self |  | Highrise | LOWER DIR | LOWER DIR |  | PO Samarbagh Rahim Abad Tehsil Samarbagh District Lower Dir | CW Kick-off Done |  |  |  | DN issuance in process | [6 empty] | Pending | 2025-03-24
54032 | North | N3 | PESCO |  | New-Self |  | Highrise | LOWER DIR | LOWER DIR | DIR | Badeen PO Samar Bagh Tehsil Samar Bagh District Lower Dir | CW Kick-off Done |  |  | 2025-02-10 | 2025-02-12 | 781,720 | [5 empty] | Pending
54035 | North | N3 | PESCO | Y2024 | New-Self | 2024-10-31 20:17 | Highrise | UPPER DIR | UPPER DIR | DIR | Kar Gabanj Akhagram Tehsil Warri District Upper Dir | CW Kick-off Done |  |  |  | DN issuance in process | [6 empty] | Pending | 2025-04-25
54037 | North | N3 | PESCO | Y2024 | New-Self | 2024-11-30 | Highrise | LOWER DIR | LOWER DIR | DIR | Sar Banda PO Kumbarh Tehsil Lal Qillah Lower Dir | Foundation In Progress | [10 empty] | Pending | 2025-04-15
54041 | North | N1 | IESCO | Y2024 | New-Self | 2024-10-13 | Highrise | ISlamabad | Islamabad | Islamabad | Islamabad New Airport Runway Coverage. | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54042 | North | N1 | IESCO | Y2024 | New-Self | 2024-12-29 23:21 | Highrise | ISlamabad | Islamabad | Islamabad | Islamabad New Airport Runway Coverage. | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54051 | North | N3 | PESCO | Y2024 | New-Self | 2024-12-23 14:39 | Highrise | Kalla Bat | Swabi | Swabi | Mohala Firdous Bnada, PO Khaas Kalabat, Topi Swabi | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54052 |  | N2 |  |  | Self |  | S&S | Peshawar | 0 |  | Cecose University Sector # H-3 Hayyat Abad Phase 2 Peshawar | CW Kick-off Done |  |  | 2025-02-10 | [7 empty] | Pending
54058 |  | N1 |  |  | Self |  | S&S | Havelian | 0 |  | Mohalla Parrao, Kholian Bala Tehsil & District Haripur | Foundation Completed |  |  |  |  | 671,906 | [5 empty] | Pending | 2025-04-25
54065 | North | North-1 |  |  | New-Self |  | Highrise | Attock | 0 | Attock | Nigah Street Darul Islam Colony House No.91, Attock City | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54069 | North | North-1 |  |  | New-Self |  | S&S | Haripur | 0 | Haripur | PO Kot Najebullah,Sarai Gadai, Tehsil & District Haripur | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54077 | North | North-3 |  |  | New-Self |  | S&S | Islamabad | 0 | Islamabad | Bhangril Kalan, PO Rawat, Tehsil & District Islamabad | Foundation In Progress |  |  |  | 2025-01-30 | 660250 | [5 empty] | Pending | 2025-03-20
54078 | North | North-1 |  |  | New-Self |  | Highrise | Rawat | 0 | Islamabad | GT Road Rawat Near Neavy Road Shahid Timber Plaza Rawat Islamabad | CW Kick-off Done | [10 empty] | Pending
54081 | North | North-3 |  |  | New-Self |  | S&S | Mansehra | 0 | Mansehra | Concred CNG, Dub no 2, Tehsil & District Manshera | CW Kick-off Done | [10 empty] | Pending | 2025-04-25
54082 |  | N3 |  |  | Self |  | ATL | Mansehra | 0 |  | Baffa Maira Road, Baffa, Mansehra | CW Kick-off Done | [10 empty] | Pending
54084 | North | North-3 |  |  | New-Self |  | S&S | Takht Bhai | 0 | Mardan | Old Sakha Kot PO Sakha Kot, Sakha Kot Tehsil Dargai and District Malakand | RFI with TCP |  |  | 2024-12-30 | 2025-01-27 | 29080 | 2025-02-04 |  |  |  | TCP | Pending
54085 | North | North-3 |  |  | New-Self |  | Highrise | Takht Bhai | 0 | Mardan | Degai Muhallah, PO Sher Ghar, Sher Ghar, Tehsil Takhat Bhai District Mardan | Excavation In Progress |  |  | 2025-02-04 | 2025-01-30 | 1,544,179 | 2025-02-14 |  |  |  |  | Pending | 2025-03-25
54086 |  | N3 |  |  | Self |  | ATL | Takht Bhai | 0 |  | Mohallah Barcham Sher Garh Tehsil Takht Bai, District Mardan | CW Kick-off Done |  |  |  | NOC Pending at CMPak |  |  | NOC Pending at CMPak End
54087 | North | North-3 |  |  | New-Self |  | S&S | Mardan | 0 | Mardan | Kaymbar, Naway Kally PO Khas Tehsil & District Mardan | CW Kick-off Done |  |  | 2025-02-10 | [7 empty] | Pending
54088 | North | North-3 |  |  | New-Self |  | ATL | Mardan | 0 | Mardan | Naray Baja PO Miltary Form Tehsil and District Mardan | On-Air |  |  | 2025-01-13 | 2025-01-14 | 1,416,962 | 2025-02-10 |  |  |  |  | Pending
54089 | North | North-3 |  |  | New-Self |  | S&S | Takht Bhai | 0 | Mardan | Mumtaz Abad Takht Bai Mardan | CWIP | [10 empty] | Pending | 2025-04-25
54091 | North | North-3 |  |  | New-Self |  | S&S | Mardan | 0 | Mardan | Koz kandain, PO Shehbaz Garhi, Bala Garhi Tehsil & District Mardan | CWIP | [10 empty] | Pending
54093 | North | North-3 |  |  | New-Self |  | Highrise | Mardan | 0 | Mardan | Meervas Sabzi Mandi Mardan | CWIP | [10 empty] | Pending
54097 | North | North-3 |  |  | New-Self |  | Highrise | Mardan | 0 | Mardan | Mohallah Boki Kot Ismail Zai, Ghari Kapoora, Tehsil & District Mardan | CWIP | [6 empty] | 2025-03-12 | Yes |  | PCP with OGC | Closed
54098 |  | N3 |  |  | Self |  | S&S | Mardan | 0 |  | New Baghdada Baghdada, Mardan | CWIP | [10 empty] | Pending
54100 | North | North-2 |  |  | New-Self |  | Highrise | Mardan | 0 | Mardan | Muhallah Mian Gan Gujrat, Tehsil and District Mardan | CWIP | [10 empty] | Pending
54101 | North | North-2 |  |  | New-Self |  | Highrise | Mardan | 0 | Mardan | Moti Banda Lund Khorr, Tehsil Takhat Bhai District Mardan | CWIP | [10 empty] | Pending
54103 | North | North-2 |  |  | New-Self |  | S&S | Pabbi | 0 | Nowshehra | Mohalla Malkan Khel, Muhib Bandha Tehsil & District Nowshera | CWIP | [10 empty] | Pending | 2025-04-25
54105 | North | North-2 |  |  | New-Self |  | Highrise | Nowshera | 0 | Nowshehra | Khawaishgi Bala Main Bazar Tehsil & District Nowshera | CWIP | [10 empty] | Pending
54106 | North | North-2 |  |  | New-Self |  | Highrise | Pabbi | 0 | Nowshehra | Fazal ur Rehman Plaza Pabbi Railway Station Tehsil Pabb District Nowshera | CWIP | [10 empty] | Pending
54109 | North | North-1 |  |  | New-Self |  | Highrise | Peshawar | 0 | Peshawar | Hinki Daman Road Salam Model School Peshawar | CWIP | [10 empty] | Pending | 2025-04-25
54115 | North | North-1 |  |  | New-Self |  | S&S | Wah+Texila | 0 | Rawalpindi | Mohallaha Malikabad, Main Jalala Road Wah Cantt Tehsil Taxila District Rawalpindi | CWIP | [10 empty] | Pending | 2025-04-25
54129 | North | North-4 |  |  | New-Self |  | Highrise | Kahuta | 0 | Rawalpindi | Near Madrisa Hasnain Village Galla Ward No.01, Kahuta Rawalpindi | CWIP | [10 empty] | Pending | 2025-04-25
54130 | North | North-4 |  |  | New-Self |  | S&S | Rawalpindi | 0 | Rawalpindi | Christian Colony Shehbaz Town,Street No. 15 Rawalpindi | CWIP | [10 empty] | Pending | 2025-04-25
54135 | North | North-4 |  |  | New-Self |  | S&S | Rawalpindi | 0 | Rawalpindi | St. 7-D Seham Social Society Shabir Lane Rawalpindi | CWIP | [10 empty] | Pending | 2025-04-25
54141 | North | North-4 |  |  | New-Self |  | ATL | Gujar Khan | 0 | Rawalpindi | Boocha PO Mandra Tehsil Gujjar Khan District Rawalpindi | CWIP | [10 empty] | Pending | 2025-04-25
54145 | North | North-2 | IESCO |  | New-Self | 2025-01-31 21:11 | Highrise | Rawalpindi | 0 | Rawalpindi | Chakri Road, Jaspal PO Raniyal, Rawalpindi | CWIP | [10 empty] | Pending | 2025-04-25
54150 |  | N2 |  |  | Self |  | S&S | Jehangira | 0 |  | Mohalla Mian Gaan Jahangira Tehsil Lahore District Swabi | CWIP | [10 empty] | Pending | 2025-04-25
54168 |  | N1 |  |  | Self |  | Highrise | Attock | 0 |  | PO Khas, Baam Khail Tehsil & District Swabi | CWIP | [10 empty] | Pending | 2025-04-25
54169 |  | N1 |  |  | Self |  | Highrise | Attock | 0 |  | Mohallah Gull Abad Near Maraqba Hall Attock | CWIP | [10 empty] | Pending
54171 |  | N1 |  |  | Self |  | Highrise | Attock Rural | 0 |  | PO Khas, Pind Mehri Tehsil Hassan Abdal District Attock | CWIP | [10 empty] | Pending | 2025-04-25
54174 | North | N1 |  |  | New-Self |  | Highrise | Attock Rural | 0 | Attock | PO khas, Kamil Pur Musa, Tehsil Hazro District Attock | CWIP | [10 empty] | Pending | 2025-04-25
54217 |  | N4 |  |  | Self |  | Highrise | Rawalpindi | 0 |  | Block C Gulberg Residencia Islamabad | CWIP | [10 empty] | Pending | 2025-04-25
54227 |  | N3 |  |  | Self |  | Highrise | Mardan Rural | 0 |  | Dobian Mardan Rd, Garhi Kapura, Mardan | CWIP | [10 empty] | Pending | 2025-04-25
54228 | North | N3 |  |  | New-Self |  | Highrise | Mardan Rural | 0 | Mardan | Mohallah Amu Khel Sari Mayyar Tehsil and District Mardan | CWIP | [10 empty] | Pending | 2025-04-25
54229 |  | N3 |  |  | Self |  | ATL | Mardan Rural | 0 |  | Muhallah Atman Khel Ghariala Tehsil & District Mardan | CWIP | [10 empty] | Pending | 2025-04-25
54230 | North | N3 |  |  | New-Self |  | Highrise | mardan | 0 | Mardan | Mohalla Shahzad Abad Guli Bagh PO Hoti Tehsil and District Mardan | CWIP | [10 empty] | Pending | 2025-04-25
54231 | North | N3 |  |  | New-Self |  | Highrise | mardan | 0 | Mardan | Mohalla Poswal Gujar Ghari District Mardan | RFI | [10 empty] | Pending | 2025-04-15
54232 | North | N3 |  |  | New-Self |  | ATL | Mardan Rural | 0 | Mardan | Mohallah Oriya Khel Ismailia Tehsil and Distirict Swabi | RFI | [10 empty] | Pending | 2025-04-15
54233 |  | N3 |  |  | Self |  | Highrise | mardan | 0 |  | Nawan Kalay PO Gujar Garhi Mardan | RFI | [10 empty] | Pending
54237 |  | N4 |  |  | Self |  | S&S | Mirpur Rural | 0 |  | PO Jattlan, New Jaboot, Tehsil & District Mirpur | RFI | [10 empty] | Pending
54238 |  | N4 |  |  | Self |  | Highrise | Mirpur Rural | 0 |  | PO Khas, Khaliq Abad Tehsil & District Mirpur | RFI | [6 empty] | Off Grid |  |  |  | Off Grid
54273 |  | N4 |  |  | Self |  | Highrise | Rawalpindi Rural | 0 |  | Dhoke Sher Zaman PO Alam Abad Gujjar Khan District Rawalpindi | RFI | [10 empty] | Pending
54285 | North | N1 |  |  | New-Self |  | S&S | Abbottabad Rural | 0 | Abbottabad | Samwala, PO Chando Mera Tehsil Havalian, District Abbotabad | RFI | [10 empty] | Pending
54289 | North | N2 |  |  | New-Self |  | Highrise | Charsadda Rural | 0 | Charsadda | Village Redewan Tehsil Tangi District Charsadda | RFI | [10 empty] | Pending
54293 |  | N2 |  |  | Self |  | Highrise | Dera Ismail Khan Rural | 0 |  | Babati Bahadry Tehsil and District DI Khan | RFI | [10 empty] | Pending | 2025-03-15
54298 | North | N2 |  |  | New-Self |  | Highrise | Peshawar Rural | 0 | Peshawar | PO Takhat Abad Jalti Payan District Peshawar | RFI | [10 empty] | Pending | 2025-03-25
54299 |  | N2 |  |  | Self |  | Highrise | Peshawar Rural | 0 |  | Ghari Ghazali Village Regi Rokizai Peshawar | RFI | [10 empty] | Pending | 2025-03-25
54300 |  | N2 |  |  | Self |  | Highrise | Peshawar Rural | 0 |  | Garanga Bala PO Chaghar Matti Peshawar | RFI | [10 empty] | Pending | 2025-04-15
54331 |  | N2 |  |  | Self |  | S&S | Peshawar Rural | 0 |  | 0 | RFI | [10 empty] | Pending | 2025-04-25
54342 | North | North-1 | IESCO |  | New-Self | 2025-01-17 | Highrise | Islamabad | 0 | Islamabad | Centauras Shoping Mall Islamabad | RFI | [10 empty] | Pending | 2025-04-25
99939 | North | N3 | PESCO |  | New-Self |  | Highrise | 0 | 0 | Buner | Mohallah Meenz Hujhrah Batara Tehsil Gagara District Buner | RFI | [10 empty] | Pending | 2025-04-25
99941 | North | N3 | PESCO |  | New-Self |  | S&S | 0 | 0 | Buner | Kozah, Hujrah Daggar District Buner | RFI | [10 empty] | Pending | 2025-04-25
99944 | North | N3 | PESCO |  | New-Self |  | Highrise | Swat | SWAT | Swat | Shinigar ton village Roringar Tehsil Matta District Swat | RFI | [10 empty] | Pending | 2025-04-25
99946 | North | N2 | PESCO |  | New-Self |  | Highrise | 0 | 0 | Kohat | Pindi Road PO Kohat, Ghulam Banda, Tehsil & District Kohat | RFI | [10 empty] | Pending | 2025-04-25
Note on O2: Dil Khurshid: Court case
Note on O40: Dil Khurshid: 53866 owner drifted the plot at the time of kick off
Note on O41: Dil Khurshid: 53847 stuck due to far end . Far end is new site and tss in progress

## Sheet2
Site ID | Region | PCP Date
53770 | North | 2025-02-16
53805 | North | Off Grid
53827 | North | 2024-09-27
53664 | North | 2024-08-24
53734 | North
53305 | North | 2024-08-20
51851 | North | Off Grid
51560 | North | 2024-05-25
53803 | North | 2024-10-18
53851 | North | 2024-12-05
53871 | North | 2025-01-07
53870 | North | 2024-11-23
53540 | North | 2024-08-12
53843 | North | 2024-12-07
53833 | North | 2025-02-13
53277 | North | 2025-01-07
53811 | North | 2025-01-07
53772 | North | 2025-01-07
53752 | North | 2024-11-23
51227 | North | 2024-04-19
53882 | North
53929 | North | Off-Grid
53944 | North
53963 | North | 2024-12-07
53966 | North | 2024-12-27
53934 | North | 2024-11-02
53698 | North | 2024-09-27
53886 | North | Off Grid
53860 | North
53846 | North | 2024-11-20
53595 | North | 2024-08-24
53960 | North | 2025-01-05
53969 | North
53946 | North
53781 | North
53984 | North | 2024-12-19
53991 | North
53999 | North
53941 | North
52479 | North | CP will be installed on 5 Mar 25
52024 | North | CP will be installed on 5 Mar 25
53924 | North | 2024-11-27
53229 | North | 2025-03-05
53762 | North | 2025-02-25
53405 | North
53948 | North | 2024-10-11
53278 | North | 2024-08-26
53927 | North | 2024-11-27
53686 | North
53964 | North | 2025-01-26
54042 | North
54041 | North
52191 | North | Off Grid
53973 | North | 2025-02-21
54078 | North
53832 | North | 2024-12-19
53173 | North | 2024-07-05
53783 | North | 2024-11-10

## SU
Site IDs | Region | City | Vendor | City | Address | CP Installation Plan Date | CP installed Actual Date
52025 | North-1 | Islamabad | S&S | Islamabad | Along Nala, Near Lal masjid, G-6/4, Islamabad. | 2024-11-21 | 3 phase meter with 25KVA PMT
53827 | North-2 | Peshawar | Highrise | Peshawar | Almas Car Village Ring Road Peshawar | 2024-07-31 | Permanent Power
50965 | North-3 | Abbottabad | S&S | Abbottabad | Gali, Dobather Rd, Abbottabad | 2024-09-03 | 3 phase meter with 25KVA PMT
52604 | North-1 | Islamabad | S&S | Islamabad | Near Road 4, Sector C, Bahria Enclave, Islamabad | 2024-07-13 | 3 Phase PP only
53760 | North-2 | Nowshehra | S&S | Swabi | Mouza Garho Khasra NO 1239 Nizam Pur Tehsil Jahangira Dist Nowshera | 2024-09-27 | 3 phase meter with 25KVA PMT
53305 | North-4 | Chakri | Highrise | Rawalpindi | Near Chakri Interchange M2,Qurtaba Road, gheela kalan, Rawalpindi | 2024-07-11 | Permanent Power
53734 | North-1 | Attock | Highrise | Attock | Ghulam Jilani, Bark Road, Attock. | 2024-07-03 | Permanent Power
53815 | North-2 | Peshawar | S&S | Peshawar | Canal Town Peshawar, | 2024-08-20 | 3 phase meter with 25KVA PMT
53579 | North-1 | Islamabad | S&S | Islamabad | Street no 15, Sector I-10/1, Islamabad | 2024-07-05 | 3 phase meter with 25KVA PMT
51560 | North-2 | Nowshera | Highrise | Nowshera | R-Main Tower. Main Nowshehra Cantt | 2024-09-12 | Permanent Power
53851 | North-3 | Swat | Highrise | Swat | Mohallah Dolat Khel, Takhta Band PO Angro Dherai, Tehsil & District Swat. | 2024-10-07 | Permanent Power
53277 | North-1 | Attock | Highrise | Attock | Near Aysha Masjid, Peoples Colony, Attock | 2024-08-30 | Permanent Power
53752 | North-3 | Mardan | Highrise | Mardan | Khawaja Ganj Bazar near Kalpani Pull Hoti Bazar Mardan | 2024-08-24 | Permanent Power
53803 | North-2 | Peshawar | Highrise | Peshawar | Mohallah Nazar abad Shaheen Muslim Town Peshawar | 2024-08-18 | Permanent Power
53811 | North-4 | Islamabad | Highrise | Islamabad | Naval Anchorage , Islamabad | 2024-08-08 | Permanent Power
53843 | North-2 | Kohat | Highrise | Kohat-Hangu | Village Ghulam Banda, Kohat | 2024-09-14 | Permanent Power
53871 | North-3 | Kanju | Highrise | Swat | Mohallah Nikar Abad Koza Banda | 2024-08-16 | Permanent Power
53412 | North-2 | Kohat | S&S | Kohat | Kohat Hangu Road, Chakar Kot, Kohat | 2024-12-10 | 3 phase meter with 25KVA PMT
53934 | North-2 | Nowshera | Highrise | Nowshehra | Barra, Gharra, Akbar Pora Tehsil Pabbi, District Nowshera | 2024-11-04 | Permanent Power
53929 | North-4 | Rawalpindi | Highrise | Rawalpindi | Old Shakrial Mohallah Sadat PO Khas, Tehsil & District Rawalpindi | 2024-09-17 | Permanent Power
53870 | North-3 | Swat | Highrise | Swat | Mona Golistan Viallage Koza Banda Tehsil Kabal District Swat | 2024-08-24 | Permanent Power
53540 | North-2 | Khyber Agency | Highrise | FATA | Main Bazar Koi Chowk Bara, Khyber | 2024-08-12 | Permanent Power
53940 | North-1 | Islamabad | Highrise | Islamabad | DHAI Teleman Sector C DHA Phase 5, Islamabad | 2024-09-10 | Permanent Power
53846 | North-2 | Kohat | Highrise | Kohat-Hangu | Masjid Bilal , Qabail Coloney, PO Kohat Jarma, Tehsil & District Kohat | 2024-11-20 | Permanent Power
53698 | North-2 | Peshawar | Highrise | Peshawar | Darmangi Bazar, Warsak Road, Peshawar. | 2024-12-02 | Permanent Power
52979 | North-3 | Mansehra | S&S | Mansehra | Dhangri, Mansehra | 2025-01-01 | TCP
52763 | North-3 | Batkhela | Highrise | Malakand | Batkhela, Malakand | No CP Applied, PDG, SOLAR SITE
53864 | North-3 | Madyan | Highrise | Swat | Shainko, PO Madyan, Tehsil Bahrain District Swat | No CP Applied, PDG, SOLAR SITE
53863 | North-3 | Bahrian | Highrise | Swat | Shagai Shahgram aryana, PO Madyan, Tehsil Bahrain District Swat | NO CP, SOLAR SITE
99944 | North-3 | Matta | Highrise | Swat | Shinigar ton village Roringar Tehsil Matta District Swat | NO CP, SOLAR SITE
53847 | North-3 | Swat | Highrise | Swat | Haqla Sar, Village behar adwo Tehsil Khawazkhela District Swat | NO CP, SOLAR SITE
53860 | North-3 | Swat | Highrise | Swat | Shalpeen, Swat. | 2024-12-05 | Permanent Power
53394 | North-3 | Mansehra | S&S | Manshehra | Ghazikot, PO Manshera, Tehsil & District Manshera | 2025-03-07
53989 | North-2 | Lakki Marwat | S&S | Lakki Marwat | Mohalla Haqdad Abad, Mena Khail, Lakki Marwat | 2024-11-23 | 3 phase meter with 25KVA PMT
54013 | North-3 | Mayar | S&S | DIR | PO Mayar, Joni Kalay, Tehsil Samar Bagh, District Lower Dir | OFF Grid
52024 | North-1 | Islamabad | Highrise | Islamabad | Service Rd W, G 11/1 G-11, Islamabad | 2024-11-02 | Permanent Power
53991 | North-3 | Lower Dir | Highrise | DIR | PO Kumber, Barkhanai, Tehsil Lalqila, District Lower Dir | 2024-12-15 | Permanent Power
54005 | North-3 | Lower Dir | S&S | DIR | Mohalla Sairai Bala PO Taza Gram Shah Alam Baba Tehsil Adenzai District Lower Dir | OFF Grid
53783 | North-2 | Peshawar | Highrise | Peshawar | Phase B Hayatabad Peshawer | 2024-11-27 | Advance Meter
53173 | North-2 | Peshawar | Highrise | Peshawar | Nawab Market, Phase 6 Hayatabad, Peshawar | 2024-11-27 | Advance Meter
53923 | North-2 | Karak | Highrise | Karak | Makori, Tehsil Banda Dawood Shah District Karak | NO CP, SOLAR SITE
53902 | North-3 | Buner | S&S | Buner | PO Dagar Tehsil Diggar District Buner | 2025-02-13 | 3 phase meter with 25KVA PMT
54030 | North-3 | Lower Dir | Highrise | DIR | PO Sammar Bagh, Kashodal, Sarala Top Tehsil Samar Bagh, District Lower Dir. | NO CP, SOLAR SITE
53861 | North-3 | Swat | Highrise | Swat | PO Khawaz Khela, Chankolai, Tehsil Khawaz Khela, District Swat. | NO CP, SOLAR SITE
53832 | North-2 | Hangu | Highrise | Kohat-Hangu | Village Tahati Banda Tehsil & District Hango | 2024-12-07 | Permanent Power
53962 | North-3 | Bajaur | S&S | Bajaur | PO Raghgan Tallay Tehsil Salarzai District Bajaur | 2025-01-07 | 3 phase meter with 25KVA PMT
99941 | North-3 | Buner | S&S | Buner | Kozah, Hujrah Daggar District Buner | OFF Grid
53941 | North-3 | Bajaur | Highrise | Bajaur | Gardai, Tehsil Utman Khel District Bajaur | 2024-12-04 | Permanent Power
53999 | North-3 | Lower Dir | Highrise | DIR | PO Aooch, Aooch Sharqi Tehsil Udan Zai District Lower Dir | 2024-12-06 | Permanent Power
53963 | North-3 | Bajaur | Highrise | Bajaur | PO Ragagan, Gidershy, Tehsil Salarazy District Bajaur | 2024-12-27 | Permanent Power
52479 | North-2 | Peshawar | Highrise | Peshawar | Phase 4 Hayatabad | 2024-12-28 | Permanent Power
53954 | North-3 | Bajaur | Highrise | Bajaur | Tangy PO Anayat Kalay Tehsil Momand District Bajaur Agency | NO CP, SOLAR SITE
53949 | North-3 | Bajaur | S&S | Bajaur | PO Khar, Markhanai Tehsil Salarzai Bajaur Agency | OFF Grid
53901 | North-3 | Buner | S&S | Buner | PO Daggar, Topadrah, Tehsil Daggar District Buner | 2025-01-07 | 3 phase meter with 25KVA PMT
50712 | North-2 | Peshawar | S&S | Peshawar | Roof Top Rmi Hospital Hayatabad, Peshawar | 2025-02-22 | Permanent Power
51179 | North-2 | Peshawar | S&S | Peshawar | Sector D 1, Street 1, Phase-1 Hayatabad | 2025-02-21 | Permanent Power
54010 | North-3 | Lower Dir | S&S | DIR | Bajarho, PO Ziyarat TalashTehsil Timergara District Lower Dir | OFF Grid
54001 | North-3 | Upper Dir | Highrise | DIR | PO Darwarra, Sarah Shah, Tehsil Dir District Uppar Dir | NO CP, SOLAR SITE
53998 | North-3 | Lower Dir | Highrise | DIR | Mohallah Ahmad Gulai, Dhrai, PO Ziarat Talash, Tehsil Timargira District Lower Dir | NO CP, SOLAR SITE
53379 | North-3 | Mansehra | Highrise | Mansehra | PO Dodhyal Shanai Bala Tehsil & District Mansehra | PCP to installed 15 March 25
53978 | North-3 | Upper Dir | Highrise | Upper Dir | Muhallah Royan Payyan PO Dir, dir Town Tehsil Dir, District Upper Dir | PCP will be installed 10 March 25
53278 | North-1 | Wah Cantt | Highrise | Wah+Taxila | Near street no 2, Along nalla, Phase 2 New City, Wah | 2025-01-01 | Permanent Power
53974 | North-3 | Bajour Agency | Highrise | Bajaur | PO Pushat Tarano Tehsil Salarazy District Bajaur | NO CP, SOLAR SITE
53686 | North-4 | Rawalpindi | Highrise | Rawalpindi | Near Main IJP Road, Dhok Hassu, Rawalpindi | 2024-11-19 | Temporary Power
54014 | North-3 | Lower Dir | Highrise | DIR | Village Kampati PO Kambarh Lal Killa District Lower Dir | NO CP, SOLAR SITE
54025 | North-3 | Lower Dir | Highrise | DIR | Muhallah Kharkani Ouch Gharbi PO Ouch Tehsil Adan Zai District Lower Dir | 2025-02-22 | Permanent Power
54004 | North-3 | Lower Dir | Highrise | DIR | Kory Naoty PO Khal Timergara Lower Dir | NO CP, SOLAR SITE
54035 | North-3 | Upper Dir | Highrise | DIR | Kar Gabanj Akhagram Tehsil Warri District Upper Dir | NO CP, SOLAR SITE
53927 | North-1 | Islamabad | Highrise | Islamabad | AD Hieghts Al-Razzaq Valley Near Pindoriyan Islamabad | 2024-12-13 | Permanent Power
52742 | North-3 | Mardan | Highrise | Mardan | Sector K Sheikh Maltoon Town, Mardan | PCP will be 3/10/2025
53229 | North-4 | Islamabad | Highrise | Islamabad | Alvi Laboratory, Jawa Road, Rawat, Islamabad | 2024-12-07 | Permanent Power
52590 | North-2 | Peshawar | Highrise | Peshawar | Aloocho Bagh, Burj Nasir Peshawar. | Dispute with PESCO,
53904 | North-3 | Buner | Highrise | Buner | Mohallah Patao, PO Jorr Chowk, Dagar District Buner | NO CP, SOLAR SITE
54012 | North-3 | Upper Dir | Highrise | DIR | PO Dir Alla Tehsil Dir District Upper Dir | NO CP, SOLAR SITE
53973 | North-3 | Bajaur | Highrise | Bajaur | Narazay PO Raghgan Tehsil Salarzai District Bajaur Agency | 2024-12-27 | Permanent Power
53969 | North-3 | Bajaur | Highrise | Bajaur | PO Raghgan Tiya Tehsil Salarazy District Bajaur | 2025-02-08 | Permanent Power
53964 | North-3 | Bajaur | Highrise | Bajaur | Shah Toot PO Raggan Balam Khar Tehsil Salarzai District Bajaur | 2025-01-26 | Permanent Power
53986 | North-1 | Attock | Highrise | Attock | Mohallah Syed Qaim Shah, PO Khas Mirza, Tehsil & District Attock | 2025-03-10
53993 | North-3 | Lower Dir | Highrise | DIR | PO Khazana, Saloband, Tehsil Sammar Bagh District Lower Dir | NO CP, SOLAR SITE
54037 | North-3 | Lower Dir | Highrise | DIR | Sar Banda PO Kumbarh Tehsil Lal Qillah Lower Dir | NO CP, SOLAR SITE
53965 | North-3 | Bajaur | Highrise | Bajaur | PO Pashat Batmalai Tehsil Salarzai District Bajaur | NO CP, SOLAR SITE
53948 | North-3 | Bajaur | Highrise | Bajaur | Loi Sum, Tehsil Khar Bajaur District Bajuar Agency | 2025-01-06 | Permanent Power
53405 | North-2 | Pabbi | Highrise | Nowshera | Banda Shekh Ismail Khan Road, Tarkha, Nowshera | 2025-02-21 | Permanent Power
54018 | North-3 | Lower Dir | Highrise | DIR | Jamia Colony, PO Sammar BaghTehsil Samar Bagh, District Lower Dir. | PCP will be installed 10 Mar 25
54002 | North-3 | Lower Dir | Highrise | DIR | Barghandho PO Kumbarh Tehsil Lal Qillah Lower Dir | NO CP, SOLAR SITE
54015 | North-3 | Lower Dir | Highrise | DIR | Maidan Bandai Lal Qila District Lower Dir | NO CP, SOLAR SITE
54008 | North-3 | Lower Dir | S&S | DIR | Kodigram Tehsil Adenzai District Lower Dir | OFF Grid
54028 | North-3 | Lower Dir | Highrise | DIR | PO Monda Ghanam Shah Tehsil Samar Bagh District Lower Dir | PCP will be installed 10 Mar 25
53908 | North-3 | Buner | Highrise | Buner | PO Khana Badal. Bodal, Tehsil Gagrah District Buner | PCP to be installed in Apr-25
54051 | North-3 | Swabi | Highrise | Swabi | Mohala Firdous Bnada, PO Khaas Kalabat, Topi Swabi | PCP will be installed 20 Mar 25
53873 | North-3 | Matta | Highrise | Swat | PO Matta, Pir Kalay Tehsil Matta, District Swat. | PCP will be installed 10 Mar 25
53866 | North-3 | Bahrian | Highrise | Swat | Torwal Kon Tatt Tehsil Bahrain District Swat | NO CP, SOLAR SITE
53947 | North-3 | Bajuar | Highrise | Bajaur | Charmang, PO Loei Sam Syeda Shah Tehsil Nawagai District Bajuar Agency | NO CP, SOLAR SITE
53912 | North-3 | Buner | Highrise | Buner | Jaffar Khel, Changlai, Tehsil Khado Khel District Buner | NO CP, SOLAR SITE
53897 | North-3 | Buner | S&S | Buner | Kankowai Tehsil Mandarh District Buner | 2025-03-07
53995 | North-3 | Lower Dir | Highrise | DIR | Mani Band, Temargara, Timergara, District Lower Dir Pakistan | NO CP, SOLAR SITE
53979 | North-2 | Peshawar | Highrise | Peshawar | NEAR ZONE 3 GOUND WATER TANK REGI Peshawar | 2025-03-25
51228 | North-1 | Wah Cantt | Highrise | Wah+Taxila | GT Rd,Asifabad wah rawalpindi | Paid DN required by CME
51227 | North-1 | Rawalpindi | Highrise | Wah+Taxila | New City Wah Cantt, Wah Cantt, Rawalpindi | 2025-02-11 | Permanent Power
54145 | North-4 | Rawalpindi | Highrise | Rawalpindi | Chakri Road, Jaspal PO Raniyal, Rawalpindi | 2025-03-05